## Lists
Status | Priority | Release
Not Started | Critical | MVP
In Progress | High | Phase 2
Done | Medium | Phase 3
Blocked | Low | Phase 4
On Hold |  | Future

## Product Roadmap
ID | Phase | Module | Item | Description / Acceptance Outcome | Priority | Target Release | Dependency | Status | Owner | Notes
P1-001 | Phase 1 - MVP | Registration & Authentication | Mobile OTP registration/login | Register and authenticate members using mobile OTP. | Critical | MVP |  | Not Started
P1-002 | Phase 1 - MVP | Registration & Authentication | Email/password login | Support secure email and password based authentication. | High | MVP | P1-001 | Not Started
P1-003 | Phase 1 - MVP | Registration & Authentication | Google social login | Allow members to register and sign in using Google. | Medium | MVP | P1-001 | Not Started
P1-004 | Phase 1 - MVP | Registration & Authentication | Email and mobile verification status | Store and display verified email/mobile states. | Critical | MVP | P1-001 | Not Started
P1-005 | Phase 1 - MVP | Registration & Authentication | Account recovery and logout | Secure password reset, token revocation and logout flow. | High | MVP | P1-002 | Not Started
P1-006 | Phase 1 - MVP | Profile Creation | Basic profile information | Name, gender, date of birth, height, weight and marital status. | Critical | MVP | P1-001 | Not Started
P1-007 | Phase 1 - MVP | Profile Creation | Religion and community details | Religion, caste, sub-caste, gotra and manglik details. | High | MVP | P1-006 | Not Started
P1-008 | Phase 1 - MVP | Profile Creation | Education details | Highest qualification, college, university and specialization. | High | MVP | P1-006 | Not Started
P1-009 | Phase 1 - MVP | Profile Creation | Career details | Occupation, employer, industry and income information. | High | MVP | P1-006 | Not Started
P1-010 | Phase 1 - MVP | Profile Creation | Family details | Parents, siblings, family type, status and values. | High | MVP | P1-006 | Not Started
P1-011 | Phase 1 - MVP | Profile Creation | Lifestyle details | Food, smoking, drinking and lifestyle preferences. | Medium | MVP | P1-006 | Not Started
P1-012 | Phase 1 - MVP | Profile Creation | Location details | Country, state, city and current residence. | Critical | MVP | P1-006 | Not Started
P1-013 | Phase 1 - MVP | Profile Creation | Horoscope details | Birth time, birth place, rashi and nakshatra. | Medium | MVP | P1-006 | Not Started
P1-014 | Phase 1 - MVP | Profile Creation | Profile photos and album | Upload, crop, reorder, moderate and control visibility of photos. | Critical | MVP | P1-006 | Not Started
P1-015 | Phase 1 - MVP | Profile Creation | Profile completion indicator | Calculate completion percentage and guide members to missing fields. | Medium | MVP | P1-006 | Not Started
P1-016 | Phase 1 - MVP | Partner Preferences | Partner preference form | Age, height, education, religion, community, location, occupation and income preferences. | Critical | MVP | P1-006 | Not Started
P1-017 | Phase 1 - MVP | Search & Discovery | Basic member search | Search active profiles using approved searchable profile fields. | Critical | MVP | P1-006 | Not Started
P1-018 | Phase 1 - MVP | Search & Discovery | Advanced filters | Age, height, religion, community, income, education, location, marital status and photo filters. | High | MVP | P1-017 | Not Started
P1-019 | Phase 1 - MVP | Search & Discovery | Sorting and pagination | Recently joined, last active, relevance and paginated results. | High | MVP | P1-017 | Not Started
P1-020 | Phase 1 - MVP | Search & Discovery | Profile detail view | Complete profile view with privacy-aware contact and photo access. | Critical | MVP | P1-017 | Not Started
P1-021 | Phase 1 - MVP | Matching | Rule-based match recommendations | Recommend members based on preferences and weighted profile attributes. | Critical | MVP | P1-016 | Not Started
P1-022 | Phase 1 - MVP | Matching | Match reason display | Explain why a profile has been recommended. | Medium | MVP | P1-021 | Not Started
P1-023 | Phase 1 - MVP | Interest Workflow | Send interest | Allow eligible members to send an interest request. | Critical | MVP | P1-020 | Not Started
P1-024 | Phase 1 - MVP | Interest Workflow | Accept or decline interest | Recipient can accept, decline or leave interest pending. | Critical | MVP | P1-023 | Not Started
P1-025 | Phase 1 - MVP | Interest Workflow | Shortlist profile | Members can save profiles for later consideration. | High | MVP | P1-020 | Not Started
P1-026 | Phase 1 - MVP | Interest Workflow | Block and report profile | Members can block communication and report suspicious profiles. | Critical | MVP | P1-020 | Not Started
P1-027 | Phase 1 - MVP | Messaging | Chat after accepted interest | Enable one-to-one text chat after mutual connection. | Critical | MVP | P1-024 | Not Started
P1-028 | Phase 1 - MVP | Messaging | Unread counts and conversation list | Display conversations, latest message and unread message count. | High | MVP | P1-027 | Not Started
P1-029 | Phase 1 - MVP | Messaging | Messaging notifications | Notify members of new interests, acceptance and messages. | High | MVP | P1-027 | Not Started
P1-030 | Phase 1 - MVP | Membership & Payments | Membership plan catalogue | Create one, three, six and twelve month plans. | High | MVP |  | Not Started
P1-031 | Phase 1 - MVP | Membership & Payments | Payment gateway integration | Securely collect subscription payments and verify callbacks. | Critical | MVP | P1-030 | Not Started
P1-032 | Phase 1 - MVP | Membership & Payments | Entitlement enforcement | Apply plan limits for interests, contact access, chat and search. | Critical | MVP | P1-031 | Not Started
P1-033 | Phase 1 - MVP | Membership & Payments | Invoices and payment history | Show payment status, invoice reference and transaction history. | High | MVP | P1-031 | Not Started
P1-034 | Phase 1 - MVP | Admin | Admin dashboard | Operational KPIs for members, profiles, payments and moderation. | High | MVP |  | Not Started
P1-035 | Phase 1 - MVP | Admin | Member management | Search, inspect, suspend, activate and soft-delete accounts. | Critical | MVP | P1-034 | Not Started
P1-036 | Phase 1 - MVP | Admin | Photo moderation | Review and approve/reject member photos. | Critical | MVP | P1-014 | Not Started
P1-037 | Phase 1 - MVP | Admin | Reports and abuse moderation | Review reports, evidence, actions and moderation history. | Critical | MVP | P1-026 | Not Started
P1-038 | Phase 1 - MVP | Admin | Membership and payment administration | View plans, transactions, failures, refunds and entitlements. | High | MVP | P1-031 | Not Started
P1-039 | Phase 1 - MVP | Admin | CMS content management | Manage FAQs, policies, help content, banners and success stories. | Medium | MVP |  | Not Started
P2-001 | Phase 2 - Trust & Verification | Identity Verification | Government ID verification | Consent-based verification using approved identity documents and service providers. | Critical | Phase 2 | P1-006 | Not Started
P2-002 | Phase 2 - Trust & Verification | Identity Verification | Selfie and liveness verification | Capture selfie, perform liveness and compare with profile identity. | Critical | Phase 2 | P2-001 | Not Started
P2-003 | Phase 2 - Trust & Verification | Employment Verification | Employment verification | Verify through company email, documents or approved providers. | High | Phase 2 | P1-009 | Not Started
P2-004 | Phase 2 - Trust & Verification | Education Verification | Education verification | Verify degree or certificate evidence with moderation workflow. | High | Phase 2 | P1-008 | Not Started
P2-005 | Phase 2 - Trust & Verification | Marital Status Verification | Divorce/widow document verification | Optional restricted document verification with strong privacy controls. | High | Phase 2 | P1-006 | Not Started
P2-006 | Phase 2 - Trust & Verification | Fraud Prevention | Duplicate account detection | Detect repeated mobile, email, device, image and identity signals. | Critical | Phase 2 | P1-001 | Not Started
P2-007 | Phase 2 - Trust & Verification | Fraud Prevention | Fake image and scam detection | Flag manipulated, stolen or suspicious images and behaviour. | Critical | Phase 2 | P1-014 | Not Started
P2-008 | Phase 2 - Trust & Verification | Trust UX | Verification badges and trust score | Display clearly defined verification states without misleading guarantees. | High | Phase 2 | P2-001 | Not Started
P3-001 | Phase 3 - AI Matching | Compatibility | Compatibility score | Calculate explainable compatibility using profile, preference and behavioural signals. | High | Phase 3 | P1-021 | Not Started
P3-002 | Phase 3 - AI Matching | Compatibility | AI match explanation | Explain common interests, goals and preference alignment. | High | Phase 3 | P3-001 | Not Started
P3-003 | Phase 3 - AI Matching | Communication | AI icebreakers | Suggest respectful first-message ideas using safe profile context. | Medium | Phase 3 | P1-027 | Not Started
P3-004 | Phase 3 - AI Matching | Communication | Conversation assistant | Suggest optional conversation starters and replies. | Low | Phase 3 | P3-003 | Not Started
P3-005 | Phase 3 - AI Matching | Profile Quality | AI profile improvement | Recommend missing profile fields, better descriptions and photo quality improvements. | Medium | Phase 3 | P1-015 | Not Started
P4-001 | Phase 4 - Safety & Privacy | Privacy | Granular photo visibility | Control photo access by all members, accepted members or approved requests. | Critical | Phase 4 | P1-014 | Not Started
P4-002 | Phase 4 - Safety & Privacy | Privacy | Phone and contact protection | Hide or mask contact details and log every reveal. | Critical | Phase 4 | P1-032 | Not Started
P4-003 | Phase 4 - Safety & Privacy | Safety | Spam and abuse detection | Rate-limit and detect spam messaging and repeated unwanted contact. | Critical | Phase 4 | P1-027 | Not Started
P4-004 | Phase 4 - Safety & Privacy | Safety | Women-focused safety controls | Allow stricter inbound communication and visibility preferences. | High | Phase 4 | P1-026 | Not Started
P4-005 | Phase 4 - Safety & Privacy | Privacy | Incognito/private browsing mode | Allow eligible members to browse without appearing in profile-view history. | Medium | Phase 4 | P1-032 | Not Started
P5-001 | Phase 5 - Premium Features | Premium Discovery | Profile boost and spotlight | Paid temporary ranking and premium visibility features. | High | Future | P1-032 | Not Started
P5-002 | Phase 5 - Premium Features | Premium Insights | Profile analytics | Show profile views, interest conversion and engagement metrics. | Medium | Future | P1-020 | Not Started
P5-003 | Phase 5 - Premium Features | Premium Messaging | Read receipts and premium communication | Add eligible messaging insights and priority communication. | Medium | Future | P1-027 | Not Started
P5-004 | Phase 5 - Premium Features | Advisory | Relationship coach and premium introductions | Offer assisted services through qualified human experts. | Low | Future | P1-032 | Not Started
P6-001 | Phase 6 - Mobile Applications | Mobile | Android application | Native or cross-platform Android application using the same FastAPI backend. | High | Future | P1-001 | Not Started
P6-002 | Phase 6 - Mobile Applications | Mobile | iOS application | Native or cross-platform iOS application using the same backend. | Medium | Future | P6-001 | Not Started
P6-003 | Phase 6 - Mobile Applications | Mobile | Push notifications | Secure device registration and configurable push notifications. | High | Future | P6-001 | Not Started
P6-004 | Phase 6 - Mobile Applications | Mobile | Biometric authentication | Use device biometric capabilities to unlock an authenticated session. | Medium | Future | P6-001 | Not Started
P7-001 | Phase 7 - Family Accounts | Family | Parent/guardian managed profile | Allow a member profile to be created or managed by an approved family member. | High | Future | P1-006 | Not Started
P7-002 | Phase 7 - Family Accounts | Family | Shared and delegated access | Provide explicit roles, permissions and audit history for family access. | High | Future | P7-001 | Not Started
P7-003 | Phase 7 - Family Accounts | Family | Family approval workflow | Allow family members to shortlist and approve potential matches. | Medium | Future | P7-002 | Not Started
P8-001 | Phase 8 - Wedding Ecosystem | Marketplace | Wedding services marketplace | List and connect users with venues, photographers, decorators and other providers. | Medium | Future | P1-032 | Not Started
P8-002 | Phase 8 - Wedding Ecosystem | Marketplace | Vendor onboarding and verification | Onboard, verify and manage service providers. | High | Future | P8-001 | Not Started
P8-003 | Phase 8 - Wedding Ecosystem | Marketplace | Lead and commission tracking | Track enquiries, conversions, commissions and vendor settlements. | High | Future | P8-002 | Not Started
P9-001 | Phase 9 - Community & Content | Content | Success stories and editorial content | Publish moderated stories, advice, help and educational content. | Low | Future | P1-039 | Not Started
P9-002 | Phase 9 - Community & Content | Community | Expert sessions and live events | Host safe moderated sessions with counsellors and domain experts. | Low | Future | P9-001 | Not Started
P10-001 | Phase 10 - AI Marriage Assistant | AI Assistant | Natural-language profile search | Search using requests such as location, profession and family-background criteria. | Medium | Future | P3-001 | Not Started
P10-002 | Phase 10 - AI Marriage Assistant | AI Assistant | Profile summarisation | Generate privacy-aware summaries of long profiles. | Medium | Future | P3-001 | Not Started
P10-003 | Phase 10 - AI Marriage Assistant | AI Assistant | Assisted matchmaking workflow | Help members compare and manage suitable profiles with explainable recommendations. | Medium | Future | P10-001 | Not Started

## Security Checklist
ID | Domain | Control | Implementation / Acceptance Criteria | Priority | Target Release | Status | Owner | Evidence / Notes
SEC-001 | Transport Security | HTTPS only | Force HTTPS and redirect all HTTP traffic. | Critical | MVP | Not Started
SEC-002 | Authentication | JWT access and refresh tokens | Use short-lived access tokens and longer-lived refresh tokens. | Critical | MVP | Not Started
SEC-003 | Authentication | Refresh-token rotation and revocation | Rotate refresh tokens and revoke used, expired or compromised tokens. | Critical | MVP | Not Started
SEC-004 | Authentication | Secure password hashing | Use Argon2id or a carefully maintained bcrypt implementation. | Critical | MVP | Not Started
SEC-005 | Authentication | OTP abuse protection | Rate-limit OTP initiation, resend and verification attempts. | Critical | MVP | Not Started
SEC-006 | Session Security | Secure cookie configuration | Use Secure, HttpOnly and appropriate SameSite cookie settings. | Critical | MVP | Not Started
SEC-007 | Web Security | CSRF protection | Protect all state-changing CodeIgniter forms and cookie-authenticated actions. | Critical | MVP | Not Started
SEC-008 | API Security | Strict CORS allowlist | Allow only approved frontend origins and required methods/headers. | Critical | MVP | Not Started
SEC-009 | Input Security | Pydantic request validation | Validate type, length, range and format at API boundaries. | Critical | MVP | Not Started
SEC-010 | Database Security | Parameterized ORM queries | Use SQLAlchemy bound parameters and prohibit string-built SQL. | Critical | MVP | Not Started
SEC-011 | Authorization | Role-based access control | Enforce member, moderator, support and administrator permissions server-side. | Critical | MVP | Not Started
SEC-012 | Authorization | Object-level authorization | Verify ownership/permission for every profile, photo, chat and payment operation. | Critical | MVP | Not Started
SEC-013 | Admin Security | Separate admin authentication and routes | Use stronger controls, restrictive access and independent audit trails for administration. | Critical | MVP | Not Started
SEC-014 | Audit | Immutable security audit logs | Record authentication, profile, moderation, payment and admin events. | Critical | MVP | Not Started
SEC-015 | Privacy | Sensitive-data minimisation | Collect only required identity, contact and profile information. | Critical | MVP | Not Started
SEC-016 | Privacy | Sensitive-data encryption | Encrypt sensitive data at rest and control key access. | Critical | Phase 2 | Not Started
SEC-017 | Privacy | Contact and photo access control | Enforce member privacy preferences and log sensitive reveals. | Critical | MVP | Not Started
SEC-018 | Media Security | Image upload validation | Validate MIME type, extension, dimensions and file signatures. | Critical | MVP | Not Started
SEC-019 | Media Security | Malware scanning and safe processing | Scan uploads and re-encode images before serving. | High | Phase 2 | Not Started
SEC-020 | API Security | Global rate limiting | Apply per-IP, per-user and per-route limits to sensitive APIs. | Critical | MVP | Not Started
SEC-021 | Secrets | Environment-based secret management | Keep secrets outside source control and rotate them periodically. | Critical | MVP | Not Started
SEC-022 | Infrastructure | Database and Redis private access | Do not expose PostgreSQL, Redis or FastAPI directly to the internet. | Critical | MVP | Not Started
SEC-023 | Infrastructure | Firewall/security-group least privilege | Expose only required ports and restrict SSH to trusted sources. | Critical | MVP | Not Started
SEC-024 | Infrastructure | Security headers | Set CSP, HSTS in production, frame, content-type and referrer controls. | High | MVP | Not Started
SEC-025 | Monitoring | Security logging and alerting | Alert on brute force, abnormal traffic, privilege changes and repeated failures. | High | Phase 2 | Not Started
SEC-026 | Backup | Encrypted database backups | Automate, encrypt, retain and periodically restore-test backups. | Critical | MVP | Not Started
SEC-027 | Lifecycle | Soft deletion and retention rules | Define account deletion, retention and legal-hold behaviour. | High | MVP | Not Started
SEC-028 | Compliance | Privacy policy and consent records | Capture policy version, consent timestamp and withdrawal events. | Critical | MVP | Not Started
SEC-029 | Dependencies | Dependency vulnerability scanning | Scan PHP, Python, JavaScript and container dependencies. | High | MVP | Not Started
SEC-030 | Testing | Security test coverage | Include auth, authorization, injection, upload and rate-limit tests. | High | MVP | Not Started

## Performance Checklist
ID | Area | Practice | Implementation / Acceptance Criteria | Priority | Target Release | Status | Owner | Evidence / Notes
PERF-001 | Web Delivery | Enable compression | Enable gzip or Brotli for compressible HTML, CSS, JS and JSON responses. | High | MVP | Not Started
PERF-002 | Static Assets | Long-lived static asset cache | Use versioned filenames and cache-control headers for static assets. | High | MVP | Not Started
PERF-003 | Media | Object storage for profile media | Store photos outside the application server and serve through CDN. | Critical | MVP | Not Started
PERF-004 | Media | Image resizing and compression | Create thumbnails and responsive variants asynchronously. | Critical | MVP | Not Started
PERF-005 | API | Pagination on list endpoints | Require bounded page size and stable sorting for all list/search APIs. | Critical | MVP | Not Started
PERF-006 | API | Avoid over-fetching | Return only required fields and avoid expensive nested data by default. | High | MVP | Not Started
PERF-007 | Database | Connection pooling | Configure bounded SQLAlchemy pools and connection health checks. | Critical | MVP | Not Started
PERF-008 | Database | Search-field indexes | Index common filters, foreign keys, statuses and sort columns. | Critical | MVP | Not Started
PERF-009 | Database | Query-plan review | Use EXPLAIN ANALYZE for expensive search and recommendation queries. | High | MVP | Not Started
PERF-010 | Database | Prevent N+1 queries | Use appropriate eager loading and query batching. | Critical | MVP | Not Started
PERF-011 | Cache | Redis caching strategy | Cache suitable master data, profile summaries and short-lived results. | High | MVP | Not Started
PERF-012 | Cache | Cache invalidation rules | Define event-based invalidation and TTL for every cached data type. | High | MVP | Not Started
PERF-013 | Authentication | Redis for OTP and rate limits | Store expiring OTP and throttling state in Redis. | Critical | MVP | Not Started
PERF-014 | Background Processing | Move slow tasks to workers | Process SMS, email, image conversion and non-critical notifications asynchronously. | Critical | MVP | Not Started
PERF-015 | FastAPI | Async for I/O-bound operations | Use async libraries where they provide a measurable benefit. | High | MVP | Not Started
PERF-016 | FastAPI | Production worker configuration | Run an appropriate number of workers based on CPU and memory measurements. | High | MVP | Not Started
PERF-017 | PHP | OPcache configuration | Enable and tune PHP OPcache in QA and production. | High | MVP | Not Started
PERF-018 | PHP | API client timeouts and retries | Set short connection/read timeouts and retry only safe transient failures. | High | MVP | Not Started
PERF-019 | Search | Search architecture evolution | Start with PostgreSQL search and define thresholds for OpenSearch adoption. | Medium | Phase 2 | Not Started
PERF-020 | Observability | Request timing and slow-query logging | Record API duration, status and slow database queries. | Critical | MVP | Not Started
PERF-021 | Observability | Resource monitoring | Monitor CPU, memory, disk, network, database and Redis metrics. | High | MVP | Not Started
PERF-022 | Testing | Load and stress testing | Test registration, search, profile view, interest and chat workloads. | High | MVP | Not Started
PERF-023 | Capacity | Define performance SLOs | Set measurable response-time, throughput and error-rate objectives. | High | MVP | Not Started
PERF-024 | Reliability | Graceful timeout and failure handling | Return safe failures when database, Redis, SMS or payment dependencies degrade. | Critical | MVP | Not Started
PERF-025 | Database | Archive and retention strategy | Prevent operational tables and logs from growing without bounds. | Medium | Phase 2 | Not Started

## MVP Deployment Order
Order | Environment | Deployment Step | Expected Outcome | Depends On | Status | Owner | Notes
1 | Local | Install WSL2 Ubuntu 22.04 | Create Linux development environment on Windows. |  | Not Started
2 | Local | Install Nginx, PHP 8.3, PHP-FPM and Composer | Prepare CodeIgniter runtime without using Spark. | 1 | Not Started
3 | Local | Install CodeIgniter 4 frontend | Install under frontend and expose only frontend/public. | 2 | Not Started
4 | Local | Install Python 3.12 and virtual environment | Create isolated backend environment. | 1 | Not Started
5 | Local | Install FastAPI dependencies | Install and freeze backend dependencies. | 4 | Not Started
6 | Local | Install PostgreSQL 16 and create development DB | Create application role, database and validate login. | 1 | Not Started
7 | Local | Install Redis | Run Redis locally and verify PONG. | 1 | Not Started
8 | Local | Configure local domains and hosts file | Configure frontend and API local DNS entries. | 2,5 | Not Started
9 | Local | Configure mkcert local SSL | Create trusted development certificate for both local domains. | 8 | Not Started
10 | Local | Configure Nginx HTTPS virtual hosts | Serve CodeIgniter and reverse-proxy FastAPI. | 3,5,9 | Not Started
11 | Local | Configure backend environment and database connectivity | Create .env and database health check. | 5,6 | Not Started
12 | Local | Configure Redis connectivity | Add Redis health check and verify backend integration. | 5,7 | Not Started
13 | Source Control | Create monorepo baseline | Commit frontend, backend, deployment configuration and master README. | 3,5 | Not Started
14 | Source Control | Configure branches and pull-request flow | Establish develop, QA and production promotion workflow. | 13 | Not Started
15 | Quality | Add linting, unit tests and integration tests | Create automated checks for PHP and Python code. | 13 | Not Started
16 | QA | Create isolated QA AWS environment | Use a separate account/VPC/resources or strong environment isolation. | 14 | Not Started
17 | QA | Configure QA DNS and TLS | Use real QA domains and trusted certificates. | 16 | Not Started
18 | QA | Deploy frontend and backend services | Deploy CodeIgniter and FastAPI with repeatable service definitions. | 16,17 | Not Started
19 | QA | Provision QA PostgreSQL and Redis | Use isolated QA database and cache; keep both private. | 16 | Not Started
20 | QA | Configure object storage for profile media | Use separate QA bucket and least-privilege credentials. | 16 | Not Started
21 | QA | Configure CI/CD to QA | Run tests and deploy the QA branch automatically. | 14,15,18 | Not Started
22 | QA | Add monitoring, logs and alerts | Centralise logs and monitor service health and resources. | 18,19 | Not Started
23 | QA | Run security, performance and UAT testing | Complete acceptance testing before production release. | 21,22 | Not Started
24 | Production | Design production network and security groups | Private database/cache, restricted SSH and public HTTPS only. | 23 | Not Started
25 | Production | Provision production application compute | Start with right-sized EC2 and keep migration path to load balancing/autoscaling. | 24 | Not Started
26 | Production | Provision managed PostgreSQL | Use RDS PostgreSQL with backups, encryption and Multi-AZ when required. | 24 | Not Started
27 | Production | Provision managed Redis | Use ElastiCache when justified by load and operational requirements. | 24 | Not Started
28 | Production | Provision S3 and CDN for media | Use private object storage, signed access and CloudFront. | 24 | Not Started
29 | Production | Configure production DNS and TLS | Use Route 53/Cloudflare and trusted certificates. | 25 | Not Started
30 | Production | Deploy hardened frontend and backend | Disable debug, optimise dependencies and run production workers. | 25,26,27,29 | Not Started
31 | Production | Configure secrets and access management | Use environment-specific secrets and least-privilege IAM. | 24 | Not Started
32 | Production | Configure automated backups and restore tests | Validate database, media and configuration recovery. | 26,28 | Not Started
33 | Production | Configure production CI/CD with approval | Deploy tagged or approved main-branch releases. | 21,30 | Not Started
34 | Production | Configure monitoring and incident alerts | Monitor availability, latency, errors, security and capacity. | 30 | Not Started
35 | Production | Conduct go-live readiness review | Security, performance, backup, rollback and business sign-off. | 23,32,34 | Not Started
36 | Production | Release MVP and monitor closely | Use controlled rollout and post-release validation. | 35 | Not Started

## Dashboard
Matrimony Product Roadmap & Delivery Tracker
Metric | Value | Area | Done | In Progress | Not Started
Roadmap Items | 76 | Product Roadmap | 0 | 0 | 76
Security Controls | 30 | Security | 0 | 0 | 30
Performance Controls | 25 | Performance | 0 | 0 | 25
Deployment Steps | 36 | Deployment | 0 | 0 | 36
How to use: Update the Status column on each tracker sheet using the dropdown. Use Owner and Notes/Evidence for accountability. Dashboard counts update automatically.